## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2195-swen-261-07b-bluepolarbears

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | NA; 2/18/20
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | NA; 2/18/20
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | NA; 2/18/20; Tested with phone and laptop. If name was taken, could not be used again.
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | NA; 2/18/20;
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | NA; 2/18/20; Tested with phone and laptop. If name was taken, could not be used again.
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | NA; 2/18/20; Tested with phone and laptop. Other device's username appears on both
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | NA; 2/18/20; First player sees 0 before signing in, 2nd sees 1.
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MD; 2/22/20
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MD; 2/22/20; User who starts a game is assigned red player, which is highlighted on the game screen
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MD; 2/22/20
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. | Pass | MD; 2/22/20; The waiting user, when selected, is sent to the game view after the app refreshes
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MD; 2/22/20; A piece can be picked up and dragged around. When hovering over a white space, that space is not highlighted and nothing happens when the piece is dropped.
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MD; 2/22/20; When a piece is dragged over a space with another piece, that space does not get highlighted, and nothing happens when the piece is dropped.
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MD; 2/22/20; When a piece is dragged to a valid space, that space gets highlighted. Note that the ability to drop a piece is not implemented yet.
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MD; 2/22/20; The red player has their pieces at the bottom. The white player has their pieces at the bottom.
As a Checkers Game, I would like to detect and highlight valid move options so that I can help the player(s) play the game.
As an AI, I would like to follow all the checkers game rules so that I can provide a fair game for the player. | Given it is the AI's turn when they make their turn then I expect it to be a valid move that follows the american rules. |  |  |  |  | Pass | DAW 4/13/20
| Given it is the AI's turn when they can make a jump move then I it to make the required jump move. |  |  |  |  | Pass | DAW 4/13/20
As a player, I would like to be able to play against an AI so that I can play alone. | Given I am signed in and not in a game when I am at the home screen then I expect to see a button or some means to start a game with an AI |  |  |  |  | Pass | MKD 4/12/20:
| Given I am in a game with an AI when I submit my turn then I expect the AI to make a move and submit their turn |  |  |  |  | Pass | DAW 4/13/20
| Given I win the game when I defeat the AI then I expect to see the victory message and an exit button. |  |  |  |  | Pass | DAW 4/13/20
As a player I would like to be able to request help so that I can know which moves I can make.
As a player I would like to be able to resign so that I can lose the game stop playing checkers. | Given I am in a game of checkers, when I hit the resign button and submit my turn then that game of checkers should end, and I should be shown an exit button. |  |  | Pass | MKD 3/31/20:
| Given I am in a game of checkers, when the other player hits the resign button then our game should end, and I should see an exit button to return me to the lobby |  |  | Pass | MKD 3/31/20:
| Given I am in a game of checkers when the other player resigns then I am shown the win display. |  |  | Pass | MKD 3/31/20: Player is notified that the other player resigned.
| Given I am in a game of checkers when I resign the game then I am shown the loss display. |  |  | Pass | MKD 3/31/20: Player is notified that they have resigned.
As a Player I want to capture all of the opponents checkers so that I can win the game. | Given I still have pieces on the board, when I jump the other player's last piece then I should win and the game should end. |  |  | Pass | MKD 3/31/20: Player is notified winner has captured all pieces
| Given I have one piece on the board, when the other player jumps it then I should lose and the game should end. |  |  | Pass | MKD 3/3/1/20: Same as above
As a Player I would like to move a piece to the opposite end of the board so that I can king my piece and move it forwards and backwards. | Given that the piece I'm moving is a simple piece when I move to a space at the complete opposite end of the board then the simple piece should turn into a king piece. |  |  |  |  | Pass | MKD 4/12/20:
| Given that I have a king piece when I drag the king piece diagonally forward or away from me to a valid space then it should be droppable. |  |  |  |  | Pass | MKD 4/12/20:
As a Player I would like to make a simple move so that I can move a piece closer to the opposite end of the board and keep playing. | Given that it is my turn to make a move when I select a single piece that has a possible forward move then I can move it to a valid forward space and end my turn. |  |  | Pass | MKD 3/31/20: Message displayed confirming move is valid.
| Given It is my turn to make a move when I select a king piece then I can move it to any open, valid space on the board that is diagonal to that piece. |  |  |  |  | Pass | MKD 4/12/20:
| Given it is my turn to make a move when I select a piece to move that has no empty valid spaces then I won't be allowed to move that piece. |  |  | Pass | MKD 3/31/20: Cannot move piece anywhere because it has no valid spaces to move to.
| Given it is my turn to make a move when I make a valid simple move then I am allowed to end my turn. |  |  | Pass | MKD 3/31/20: Submit turn button is lit up and able to be clicked to end turn.
As a Player I would like to sign out so that I can stop playing checkers. | Given I am signed in when I am at the home screen then I expect to a see a button to sign out. |  |  | Pass | MKD 3/31/20: Button is located at the top left once signed in.
| Given I was signed in when I click the sign-out button then I expect to be returned to the Home Screen. |  |  | Pass | MKD 3/31/20:
| Given I am signed out when I am at the home screen then I expect to be able to sign in again. |  |  | Pass | MKD 3/31/20:
As a Player I would like to make a jump move so that I can capture an enemy piece and move further on the board. | Given it is my turn and I select a single piece when I try to jump a piece backwards then the game does not allow me to make that move. |  |  | Pass | MKD 3/31/20: Move is noted as invalid
| Given I select a single piece that has a valid forward jump when I jump that piece then my single piece is moved to that new space, and my opponents piece is removed from the board. |  |  | Pass | MKD 3/31/20:
| Given it is my turn when I try to jump over my piece then I see some warning showing that it is an invalid move. |  |  | Pass | MKD 3/31/20: You cannot even place your piece jumping over one of your own pieces.
| Given it is my turn when I select a piece that has only one possible jump then after the jump is complete, I can end my turn. |  |  | Pass | MKD 3/31/20:
| Given it is my turn when I select a piece that has a valid multiple jump then the pieces that I jumped are removed from the game and my turn ends. |  |  | Pass | MKD 3/31/20
As a Player in a game, I want to check whose turn it is so that I can take my turn when the other player submits their turn. | Given I am waiting for the other person to make their turn and their turn is still happening when the game refreshes then the game board should still be the same and I will continue to wait for my turn. |  |  | Pass | MKD 3/31/20: Everything still works when the game refreshes, and it is still the opponent's turn.
| Given I am waiting for the other person to make their turn and they finish their turn when the game refreshes then the board should update with the new move and it should be my turn. |  |  | Pass | MKD 3/31/20:
| Given I am waiting for the other person to make their turn and they resign when the game refreshes then I should see a message saying that the other player has resigned. |  |  | Pass | MKD 3/31/20:
As a Player I want to interact with the game through buttons so that I can submit or backup my current move. | Given it is my turn when I finish placing my move then I expect to be able to submit my turn through the submit button. |  |  | Pass | MKD 3/31/20: Turn submitted message displayed to confirm success of the turn submission.
| Given it is my turn when I finish placing my move then I expect to be able to back up my move through the backup button. |  |  | Pass | MKD: 3/31/20: Backup submitted message is displayed to confirm the backup success.
| Given it is not my turn when I am viewing the game screen, then I expect to not be able to click the submit or backup buttons |  |  | Pass | MKD 3/31/20: Buttons are greyed out and cannot be clicked when it is not your turn.
As a Player I want to force the player to have no valid moves so that the game can end and I can win. | Given it is my turn when I have no possible moves to make then I will lose and the game ends |  |  |  |  | Pass | MKD 4/12/20:
| Given it is my opponent's turn when my opponent has no valid moves then I will win and the game ends |  |  |  |  | Pass | MKD 4/12/20: